## W#26
ePOSTouch - Week #26, 2011
Report date: 02-07-2011
Reporter: Nguyen Nhat Thanh
General Status
Task status
# | Tasks | Priority | Start date | Forecast date | Actual date | Status | Remark - Delivery(doc, Source) - Link(SVN) | Owner
1 | HTML-POS | High | 2011-05-16 | 2011-05-27 | 2011-05-27 | Done
2 | SmartBizPOS Restaurant Proposal | Low | 2011-06-06 | 2011-06-09 | 2011-06-09 | Done
3 | Setup SmartBizPOS to A.Son-PC | Medium | 2011-06-20 | 2011-06-20 | 2011-06-20 | Done
4 | R&D - Magnetic Card | Medium | 2011-06-27 | 2011-06-29 |  | On going
4 | R&D - MerchantWARE | High | 2011-06-30 | 2011-07-01 |  | On going
Plan for next week: delivery on 06-July & 08-July
# | Tasks |  | Start date | Forecast date | Remark |  |  | Owner
1 | SmartBizPOS: English + Starbuck-Data |  | 2011-07-04 | 2011-07-05 | Starbuck Product, Price, …
2 | Magnetic Card |  | 2011-07-06 | 2011-07-08 | Visa, Master, Amex. Gift card (pending)
3 | MerchantWARE |  | 2011-07-11 | 2011-07-15 | Release both standalone app + SmartBizPOS with MerchantWARE
Risk/ Action
# | Risk name |  |  |  | Action
1
2
Issue/ Action
# | Issue name |  | Type of issue | Severity | Closing date | Action |  | Owner
Note on B7: Green, Yellow, Red
Note on D10: Low, Medium, High
Note on E10: dd-mm-yyyy
Note on F10: dd-mm-yyyy
Note on G10: dd-mm-yyyy
Note on H10: On-hold, On going, Done
Note on E18: dd-mm-yyyy
Note on F18: dd-mm-yyyy
Note on E35: Technical, Management, Quality
Note on F35: Low, Medium, High
Note on G35: dd-mm-yyyy

## W#Week
<Project Name> - <Team Name> - Week #<No.>, <Year>
Report date: <Date>
Reporter: <Reporters>
General status
Task status
# | Tasks | Priority | Start date | Forecast date | Actual date | Status | Remark | Owner
Plan for next week
# | Tasks |  | Start date | Forecast date | Remark |  |  | Owner
Risk/ Action
# | Risk name |  |  |  | Action
Issue/ Action
# | Issue name |  | Type of issue | Severity | Closing date | Action |  | Owner
Note on B7: Green, Yellow, Red
Note on D10: Low, Medium, High
Note on E10: dd-mm-yyyy
Note on F10: dd-mm-yyyy
Note on G10: dd-mm-yyyy
Note on H10: On-hold, On going, Done
Note on E19: dd-mm-yyyy
Note on F19: dd-mm-yyyy
Note on E36: Technical, Management, Quality
Note on F36: Low, medium, High
Note on G36: dd-mm-yyyy